Hannahwood Mews Improvements

Current notes as follows:

Budget of approx. £50,000 (from Legacy funding), works & costs to be spread over period May to September / October 2026.

Important to have an agreed action plan that can work to a realistic target & budget, agreed by team and main stakeholders.

Phase 1 (quick improvements – to living and dining area + conservatory), Phases 2 & 3 e.g. internal painting in warmer months where windows can be left open, external painting also when dryer / warmer weather.

The plan shows some of the thinking visually, this will be updated and improved as things are finalised. The new lobby & corridor is a potential Stage 2 improvement, subject to funding.

Current works, planned / being planned:

- Repairs to new kitchen work top behind sink. Completed 20/02/26.

- KP to arrange for a declutter and clearance of non-essential items in corridors and social areas (supported by Maintenance). Many items no longer required and make areas look cluttered. Required to improve the home and make works easier to manage. Clear all walls, especially in corridors & clear alcoves as could be used for storage of Adult Chairs and new PPE stations. Clothes drying to be moved upstairs so not in Conservatory. Remove all equipment that is no longer used, especially when fitted to walls. Staff coats & bags all upstairs

- Better separation hot water and heating system, improved pipework, to have significantly improved heating and hot water. B & R Heating being booked in to carry out necessary work. Maintenance will be supporting further improvements. Completed 24/04/26.

- JH planned move to AA’s bedroom (when AA moves to EGH during May), decoration required. This room likely to remain vacant as cold with current main entrance, issue for this room on this corridor.

- Clear out conservatory so can be used as a 2nd living area, items to be stored in other areas.

- Upstairs staff toilet, flooring required so can be operational again.

- Medication units for each resident, purchased and to be installed.

Agreed and costed works can be planned for May to September/October 2026, will require DH Maintenance and some external contractors, working to plan/budget:

- Strip out dining room area of all existing units and equipment. Discuss and agree with team need for further units – not sure more storage is needed.  A dining area created, clear of other units / equipment.

- In dining room plastic to be removed from walls, to review and see state of walls. Ideally replastered and painted but depends on state.

- Move living room door from corridor from the far left to the far right (looking at wall from in living room), this will help have the living room less like a corridor area to the kitchen and dining area.

- Kitchen, dining room, living room, conservatory new flooring. Look at carpet on stairs. Review all areas as some ‘joins’ currently not looking good.

- New fire doors to be painted, white, to review and fix some of the new woodwork as coming off walls.

- Replastering where required & painting of living room, dining room, conservatory, and corridors. White in conservatory & corridors, choice required for living room & dining room paint colour.

- Review lighting, especially in social areas, LEDS (re-active lighting to be planned.

- Individual bedrooms decorated, a phased approach based on need & choice.

- All square plastic/foam squares to be removed from walls and ceiling.

- New blind slats for the conservatory.

- All windows on route to new entrance to have external view tint only.

- PPE station, one in 8 bed corridor and one in 4 bed corridor, in alcove areas.

- Emergency exit door by downstairs toilet, not sealed around the edges, likely new door required. Potential for this to be the staff entrance / exit when not with residents.

- External doors on other side of conservatory to be replaced.

External Jobs:

- Maintenance / Potentially an External contractor to clean and paint the whole building – timing and best use of resource TBC?

- The gutters and conservatory need a good clean and then this is to be done regularly. Minor work required to prevent leaks.

- Solar panels on front lower roof, from recently confirmed grant. Separately funded and will reduce costs moving forwards. By March 2027.

Potential New Furniture:

- Larger fridge freezer in kitchen so not needed in ‘dining room’. If further freezer required there is room in hallways for this when other items are removed.

- New dining table & chairs

- New sofa

- New table for conservatory

- New ‘larger TV’ potentially on wall to save space in living room. Depends how furniture laid out.