## Works
Hydro | Cant Start until Rio clear |  |  |  | Mews
Contractor |  | In House |  | Materials | Contractor |  | In House | Materials
Filter | ISCA | Pipework radiator + Underfloor | Rio | Screed | New Entrance Door | Securidoor | Dining Area rip out | Paint - Lots of it!
Crumb Floor | ISCA | Chisel up tiles | Rio | Carpet Tiles | Plastering Dining Area | ??? | Paint whole internal walls ceilings | Fridge Freezer
Grates | ISCA | Screed + Carpet Tiles | Rio | Paint | Kitchen, Dining, Conservatory, Stairs, Living Room flooring | Ivybridge carpets | Paint internal doors | Dining Table + Chairs
Entrance Rio | PHM + Securidoor | Brickwork under window + external path? | Rio | Storage? Custom or off shelf | Internal lighting | MCE | Clean conservatory | Sofa
Changing room floor | Ivybridge carpets | Fire doors corridor + Timer | Rio | Tanking for walls in pool | External lighting | MCE |  | Table for Conservatory
Changing room lights | MCE | Built in storage | Rio | Fire doors and frame + closers | Clean exterior | ??? |  | TV
Lighting Rio | MCE |  |  |  | Paint Exterior | ???
|  | Remove Panelling + Tiles | Changing Rooms
|  | Chisel up tiled floor | Changing Rooms
|  | Repair / Replace doors | Changing Rooms
|  | Pipework for showers | Changing Rooms
|  | Storage | Changing Rooms
|  | Panelling around room | Changing Rooms
|  | Cubicles? | Changing Rooms
Remove Lighting rig
Clean up pool cover rollers
Create barrier between crumb floor and wall - tanking
Modify small changing room doors

## Timeline
Project Planning Guide - Hydro + Mews 2026-2027
Hydropool 20th April Deadline
|  | March |  | April |  | May | June | July | August | September | October | November | December | January | February | March
In house | Hydropool |  | Rio | Pipework radiator + Underfloor | Rio | Doors blocked up
|  |  |  | Chisel up tiles |  | Walls boarded skimmed
|  |  |  | Screed + Carpet Tiles |  | Decorating
|  |  | Changing Room 1 | Remove Panelling + Tiles | Changing Room 2 | Remove Panelling + Tiles
|  |  |  | Repair / Replace doors |  | Repair / Replace doors
|  |  |  | Pipework for showers |  | Pipework for showers
|  |  |  | Panelling around room |  | Panelling around room
Remove Lighting rig
Create barrier between crumb floor and wall - tanking
Modify small changing room doors
Fire doors corridor + Timer
| Mews |  |  |  |  | Decorating | Decorating | Decorating | Decorating | Decorating
Contractor | Hydropool |  | ISCA | Filter | PHI + Securidoor | New Windows + Sliding Door Entrance
Crumb Floor
Grates
|  |  | MCE | Changing room lights
Lighting Rio
Mews
|  |  |  | Refurb dining room |  |  | New Flooring | New Rear door and staff entrance
New living room entrance from corridor
Phase 1

## Cover
| Staff Cover |  |  |  |  | Water Babies 1st Deadline
| 16/3 - 22/3 | 23/3 - 29/3 | 30/3 - 5/4 | 6/4 - 12/4 | 13/4 - 19/4 |  | 20/4 - 26/4
Dave H |  | In | In | In | In |  | In
Paula | In | In | In | In | In |  | In
Clay | In |  |  |  | In |  | In
Dave (3 Days) | In |  | In | In | In |  | In
Trev (3 Days) | In | In | In | In | In |  | In